## Sheet1
Legend:
| Project Start Date: |  | 2021-03-15 |  |  |  |  | Completed |  |  |  | Low Risk |  |  |  | Med Risk |  |  |  | High Risk
Gantt Chart
[6 empty] | March | [20 empty] | April
[6 empty] | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26
[6 empty] | Week 1 | [6 empty] | Week 2 | [6 empty] | Week 3 | [6 empty] | Week 1 | [6 empty] | Week 2 | [6 empty] | Week 3 | [6 empty] | Week 4
Milestone Description | Category | Assigned To | Progress | Start | No. Days
Create Java Project | Completed | Adarsh Koka | 100% | 2021-03-15 | 1 | bar: March 15
Create GitHub Repository | Completed | Adarsh Koka | 100% | 2021-04-04 | 1 | bar: April 4
Add Maven Dependancies | Completed | Adarsh Koka | 100% | 2021-03-20 | 10 | bar: March 20 to March 30
Demonstrate access to obesity data from API | Completed | Adarsh Koka | 100% | 2021-03-20 | 31 | bar: March 20 to April 12
Create method createData() | Completed | Adarsh Koka | 100% | 2021-04-15 | 10 | bar: April 15 to April 25
Create method getData() | Completed | Adarsh Koka | 100% | 2021-04-15 | 10 | bar: April 15 to April 25
Clean data and put into Arrays | Completed | Adarsh Koka | 100% | 2021-04-19 | 1 | bar: April 19
Build JavaScript frontend | Completed | Adarsh Koka | 100% | 2021-04-22 | 3 | bar: April 22 to April 24
Create selectors checklist for diseases | Completed | Adarsh Koka | 100% | 2021-04-22 | 3 | bar: April 22 to April 24
Set up listeners for selected diseases | Completed | Adarsh Koka | 100% | 2021-04-22 | 3 | bar: April 22 to April 24
Create JavaScript methods for Bar Chart visualization | Completed | Adarsh Koka | 100% | 2021-04-22 | 3 | bar: April 22 to April 24
Create JavaScript methods for Pie Chart visualization | Completed | Adarsh Koka | 100% | 2021-04-22 | 3 | bar: April 22 to April 24
Test different selected diseases | Completed | Adarsh Koka | 100% | 2021-04-25 | 1 | bar: April 25